## Slide 1
6/3/2015l Pierre Roux Air Liquide Advanced Technologies
G&C Large Helium refrigerators
Increasing Competitiveness and profit
DESIGN TO COST –Progress
THIS DOCUMENT IS CONFIDENTIAL

## Slide 2: WP1 – Product / Modularisation
Functional Analysis & Modularisation  Overall schematic done
PID = Base of module interfaces and discussion for DTC.
   Implication of Clément GIRE to implement benefits of Helial
   First item : define the best tool
   Start to draft the DTC PID (remove all non necessary components) still pending

## Slide 3: WP3 – Compression & ORS & Dryer / Purifier
Compression
  Datasheets for 5 / 10 / 25 kW refrigeration plant & TMCP provided to suppliers.
  Discussion with Mycom / Aerzen / Kobelco
  Minimum components to identified  requested PID to supplier
    Mycom received / Waiting for Aerzen à relancer / Kobelco for 15/06/2015
  New manufacturer -> Frick & GEA beginning of july
Coalescers / Charcoal Tower
  Clarification of oil content at compressor outlet (15 ppm mini to 0.5 ppm)
  Sizing simple but criteria still to be clearly defined  standard to be issued.

## Slide 4: WP6 – Cold Box Design
Process
  Process 5 kW / 10 kW / 25 kW done. (close to estimations)
HX
  First HX calculated to provide a estimated size.
Module adsorber 80K : Augustin & Noelle
  3 sizes define for ads 80K : Noelle  Done, Regeneration to be done.
  Regeneration loop / Methods under evaluation by Augustin
ORS
  Clarification of oil content at compressor outlet (15 ppm mini to 0.5 ppm)
  Sizing criteria still in discussion  standard to be issued.
Components
  TVO identified to be investigated
  Cryovalves : some suppliers identified but still to be investigated.